## jobs
job_id | job_data
1 | [{"job_id":1,"customer":"Max","site":"6 Cliff Parade","cs_number":"123","dwg_number":"456","start_date":19156,"required_by":19184,"hours_mill":5,"hours_program":10,"hours_cnc":15,"hours_veneer":20,"hours_bench":25,"hours_spray":30,"hours_dispatch":35,"active":1,"created_by":"a117644@r02.xlgs.local","created_on":"2022-06-13 15:28:36","updated_by":"a117644@r02.xlgs.local","updated_on":"2022-06-13 15:28:36","start_date_mill":19156,"days_mill":1,"end_date_mill":19157,"start_date_program":19157,"days_program":2,"end_date_program":19163,"start_date_cnc":19163,"days_cnc":3,"end_date_cnc":19166,"start_date_veneer":19166,"days_veneer":3,"end_date_veneer":19171,"start_date_bench":19171,"days_bench":4,"end_date_bench":19177,"start_date_spray":19177,"days_spray":5,"end_date_spray":19184,"start_date_dispatch":19184,"days_dispatch":5,"end_date_dispatch":19191,"days_overrun":7,"start_date_recommended":19149}]
2 | [{"job_id":2,"customer":"Kerry","site":"6 Cliff Parade","cs_number":"321","dwg_number":"654","start_date":19158,"required_by":19173,"hours_mill":5,"hours_program":0,"hours_cnc":0,"hours_veneer":10,"hours_bench":10,"hours_spray":10,"hours_dispatch":1,"active":1,"created_by":"a117644@r02.xlgs.local","created_on":"2022-06-13 16:00:50","updated_by":"a117644@r02.xlgs.local","updated_on":"2022-06-13 16:00:50","start_date_mill":19158,"days_mill":1,"end_date_mill":19163,"start_date_program":19163,"days_program":0,"end_date_program":19163,"start_date_cnc":19163,"days_cnc":0,"end_date_cnc":19163,"start_date_veneer":19163,"days_veneer":2,"end_date_veneer":19165,"start_date_bench":19165,"days_bench":2,"end_date_bench":19167,"start_date_spray":19167,"days_spray":2,"end_date_spray":19171,"start_date_dispatch":19171,"days_dispatch":1,"end_date_dispatch":19172,"days_overrun":0,"start_date_recommended":19158}]
3 | [{"job_id":3,"customer":"Alex","site":"Brighton Avenue","cs_number":"666","dwg_number":"0","start_date":19180,"required_by":19208,"hours_mill":25,"hours_program":10,"hours_cnc":20,"hours_veneer":0,"hours_bench":10,"hours_spray":0,"hours_dispatch":1,"active":1,"created_by":"a117644@r02.xlgs.local","created_on":"2022-07-07 17:37:37","updated_by":"a117644@r02.xlgs.local","updated_on":"2022-07-07 17:37:37","start_date_mill":19180,"days_mill":4,"end_date_mill":19186,"start_date_program":19186,"days_program":2,"end_date_program":19188,"start_date_cnc":19188,"days_cnc":3,"end_date_cnc":19193,"start_date_veneer":19193,"days_veneer":0,"end_date_veneer":19193,"start_date_bench":19193,"days_bench":2,"end_date_bench":19195,"start_date_spray":19195,"days_spray":0,"end_date_spray":19195,"start_date_dispatch":19195,"days_dispatch":1,"end_date_dispatch":19198,"days_overrun":0,"start_date_recommended":19180}]